## Register (Print)
Risk Register - January 2017
Ref | Count | Description | Type | Trend | Likelihood | Likelihood Score | Impact | Impact Score | Inherent Risk Score | Control Adjustment | Residual Score | Risk Rank | Risk Owner | July 2016 Update
R1 | 6 | Failure to achieve income targets | Operational |  | Medium | 2 | Very High | 5 | 10 | 0 | 10 | 5 |  | The rating scores for this risk remain unchanged - the tracking of income through the current year and the development of income streams for the indiactive 2017/18 budget will be significant factors.
R2 | 7 | Failure to actively engage with member schools | Strategic |  | Medium | 2 | Very High | 5 | 10 | 0 | 10 | 5 |  | This risk score for this has decreased - membership is not almost 100% and engagement is higher than previously. The remaining risk factor is the maintaining of engagement through the school improvement cycle.
R3 | 20 | Failure to comply with legilation - health and safety legislation | Strategic |  | Medium | 2 | Very High | 5 | 10 | 0 | 10 | 5 |  | Policy, training, independent audit and risk assessments all in place - risk levels unchanged.
R4 | 4 | Failure to maintain good working relationship with Sheffeild City Council | Operational |  | Medium | 3 | Very High | 4 | 12 | 0 | 12 | 3 |  | The overall scores for this risk has increased since the last report so an explanation should be given of whether it is the 'likelihood' or 'impact' or both which have increased. For example the impact rating may have been increased because the key post at SCC is currently vacant.
R5 |  | Directors Profile - high profile which may cause Learn Sheffield to attract publicity | Strategic |  | Medium | 3 | Medium | 3 | 9 | 0 | 9 | 8 |  | This risk is increased both strategically by the comms strategy (increasing profile and working relationship with the media) and through the AGM/EGM process and the election of a substantive board.
R6 |  | CEO / Senior Staff absence risk | Strategic |  | Medium | 3 | Very High | 5 | 15 | 0 | 15 | 2 |  | Delayed expansion of capacity delays the mitigation through having a larger senior staff team.
R7 |  | Pension Risk | Financial |  | Very High | 5 | High | 4 | 20 | 0 | 20 | 1 |  | Unchanged as a risk to tolerate - to be reviewed post TUPE transfer
R8 |  | HR Risk | Compliance |  | Medium | 3 | High | 4 | 12 | 0 | 12 | 3 |  | TUPE transfer effective 01.09.16. Need to ensure access to high quality HR support / advice to ensure compliance for existing and new staff members.

## Definitions
Likelihood |  | Impact |  | Controls
Category | Score | Category | Score | Category | Score
Very High | 4 | Very High | 4 | Good | -4
High | 3 | High | 3 | Satisfactory | -3
Removed | 0 | Removed | 0 | Inadequate | -2
Medium | 2 | Medium | 2 | Weak | -1
Low | 1 | Low | 1 | None | 0